## Cover Page
KOGI STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) 2025 |  | PROGRESS REPORT
State: |  | KOGI
Reporting period: |  | FY 2025
SABER Focal Person: Mukadam Asiwaju Asiru Idris FCA | Hon Aliyu Nda Salami
List of contributing entities: | Ministry of Finance, Budget and Economic Planning, Ministry of Commerce and Industries, Ministry of Justice, State Judiciary, Kogi State Town Planning Board, Kogi State Internal Revenue Service, Land and Survey, Kogi State Investment Promotion and Public Private Partnership Agency (KOSIPPPPA), Kogi State Utility Infrastructure Management & Compliance Agency, Kogi State Geographic Information System, Kogi State Chamber of Commerce Mines & Industries (KOCCIMA).
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date: |  |  | 2026-07-28

## BERAP 2025 PROGRESS REPORT
KOGI STATE 2025 BUSINESS ENABLING REFORM ACTION PLAN PROGRESS REPORT
Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | List of Private Sector Contributors | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
1 | Improved transparency and sustainability in the property registration and land investment process | 1. Identify the physical addresses of all Residences in a Classified Area/ settlements, including the physical addresses for Apartment Residents; 2. To attempt to locate the addresses for Persons who own the Residences, if they do not reside at the Residence; and 3. To attempt to locate individuals who previously resided at and/or owned a Residence within the Area during the Class. 4. Ensure Urban observatory, improve security of properties and live, aid physical planning and control, provision of physical infrastructures and a booster to revenue generation. 5. Digitize property database, online application and allocation. | 1. Sensitize property owners on the need for their property records to be registered on the Kogi State Geographic Information System (KOGIS) database. 2. Publishing Radio jingles, Social Media and fliers organizing town hall meetings. 3. Mapping/basemap of kogi state 4. Carry out Property identitfications implementation across the entire State, using mobile hand held devices with specialized application. 5. Training and deployment of adhoc staff. 6. Automation of Property database in the State. 7.Integration of property database with KGIRS payment portal. | To identify & capture 70% of landed properties {building and structures} Government and Private Properties: Including industries , hotels, plazas, Parks, Homes etc. | Bureau of Lands | Ministry of Housing and Urban Development, Kogi State Geographic Information System (KOGIS), Kogi State Internal Revenue Service (KGIRS), Kogi State Investment Promotion and Public Private Partnership Agency (KOSIPPPPA) , Town Planning & Development Board. | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) Kogi State Traders Association | N500,000,000 | 2025-01-01 | 2025-12-01 | DELAYED | 55000 Properties were identified and captured. 12 Local Government Area already captured out of 21. 12 Sensitisation sessions were carried out in 2025. 6 slots of radio jingles were sponsored Live radio programs were carried out Bureau of Land Database successfully integrated with the KGIRS Portal. Reasones for delay in completing the activities within the 2025 implementation timeframe are as follows: 1. On commencement of stakeholders engagagement to access adequate information and permission we encountered resistance from property owners and had dificulties in assesing the properties for valuation. 2. Sensitization process equally contributed to the delay as all channel of disemination of information are required for wider coverage. 3. Insecurity in some part of the State limiting the process. | Updating the automated property database and quality assurance with comleteion timeframe between October - December 2026 Continuous Capacity training of staff, a quartelly trainign target has been set annually. Complete Basemap/mapping of the entire State by first quarter of 2027 Enumeration of 10 other Local Government areas in the State has commenced and should be completed by September 2026 Monthly sensitization of the general public on the enumeration of properties.
2 | To Ease Fibre Optics Infrastructural Investments To Private Investors In Kogi State. | 1. Improve businesses access to internet , skills and up-to-date information. 2. Increase fibre optics deployment in Kogi State. | 1. Meeting with Telecom service providers, regulators and investors to increase Fibre optics deployment. 2. Registration of Investors; Liscensing of new telecom service providers and approval of permits for right of way. 3. Information management in respect of geographical Information system. 4.Training & capacity building of staff. 5. Development of a robust one-stop -shop website. | 1. Mapping of 250km of fibre optic cables routes and utility right of ways in conjunction with telecoms and other service providers. 2. Training of 20 staff on industry knowlegde. 3. Engage the services of a consultant to develop the agency website. | Kogi State Utility Infrastructure Management & Compliance Agency | Ministry of housing and urban development, Bureau of Lands, KGIRS, Kogi State Information and Technology Agency (Kogi SITDA). | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N350,000,000 | 2025-01-01 | 2025-12-01 | DELAYED * Development of Agency website is still in progress. * Capacity traing for members of staff was not held in 2025 but plans are on ground to organise one within 2026 | 7 meeting sessions were held with service providers in 2025 as follows: 3 Meetings with MTN 2 Meetings with Glo 2 with Airtel. One Right of way licensed was issued to global independent connect Limited 5074m of fibre optics deployment at N145 per linear meter. Fibre Optics routes mapping and joint audit was conducted and completed by the State in conjunction with the Service providers in 2025. Note: The reasons for delays in completeion of the agency website is due the policy of the state to harmonise and host all State MDAs on a single domian. | Completion of Agency website between July-December 2026 Digitzation of process and workflow of the agency by the end of 2026. Capacity training of staff between July - December 2026
3 | Increased transparency of official fees and procedures | 1. Publish the approved fees and rates on the State website, Radio, Print and Electronic media for public awareness. 2. Establish a Greiviance redress mechanism for dispute resolution. | 1. Continuous enagagement/ enlightment of the public on the published laws, rates,fees, charges and procedures through social media platforms, radios and Television stations. 2. Activate the Grievance Redress Mechanism (GRM) to receive and address complains from Business operators and the general public. | 1. 144 slots of Radio and TV jingles for continous public awareness. 2. Atleast 52 sessions of GRM annually. | Ministry of Commerce and Industry | Kogi State Internal Revenue Service (KGIRS), Ministry of Justice, Kogi Chamber of Commerce Industry Mines & Agriculture (KOCCIMA) | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N15,000,000 | 2025-02-01 | 2025-12-31 | COMPLETED visit www.taxpayers.irs.kg.gov.ng for more details 4 NOS GRM OFFICES ACTIVATED ACCROS THE THREE SENATORIAL REGION NAMELY OKENE, KABBA ANYIGBA AND LOKOJA RESPECTIVELY. | • 450 slots of jingles were done at different dates as at December 31st 2025. 4 Nos Grievance Redress Mechanism offices activated across the three senatorial districts namely Okene, Kabba, Anyigba and Lokoja respectively • 72 disputes were resolved in total through activated Grievance Redress Mechanism offices situated in KGIRS Tax offices (Lokoja, KABBA, Ayingba and Okene) across all business sectors under the GRM. • Toll free number has been set up for the 4 Tax Offices: I. Head Office 07056990041 II. Ayingba 07056990125 III. Okene 07056990126 IV. Kabba 070569901271. * 2 Nos awareness sensitization sessions were carried out. * Public awareness activties were successfully carried out through social media platforms and other communication channels to educate stakeholders on the approved laws, rates, fees, charges and procedures. | 1. 1000 slots of radios and jingles for continuous public awareness in 2026. 2. Extending GRM to 7 remaining KGIRS Area Tax offices in the State. 3. Sustain regular public enlightenment campaigns and update stakeholders on any changes to relevant laws, rates, fees, charges, and procedures. 4. Continue to strengthen the grievance redress mechanism, monitor response times, and ensure timely resolution of complaints to improve the business environment.
4 | Increased Transparency of fees & levies for inter-state trade and increased export certification | 1. Increase ease of doing business across the State using the state harmonized tax law. 2. Activate existing export promotion committee. 3. Establish taskforce to enforce compliance. | 1. Dismantle all illegal road blocks where produce levy are collected. 2. Encourage establisment of cooperative organizations. 3. Monitor warehouses for grading, sorting and certification of produces for exports | 1. Haulage Fees will be collected at the point of Loading and Offloading. 2. Export Certification will be fully automated. | Ministry of Commerce and Industry | KGIRS, KOCCIMA, Kogi State Commodity, Export Promotion and Market Development Agency, Ministry of Information and communication. | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N50,000,000 | 2025-02-01 | 2025-12-12 | COMPLETED | 1. All identified illegal roadblocks used for unauthorized collection of produce levies were successfully dismantled, and relevant stakeholders were sensitized on compliance with approved revenue collection procedures. 2. Awareness campaigns and stakeholder engagements were carried out, leading to the formation and strengthening of co-operative organizations among producers and traders. 3. Routine inspections and monitoring exercises were conducted to ensure warehouses comply with required standards for grading, sorting and certification of produce intended for export. | 1. Conduct periodic surveillance and monitoring to prevent the re-establishment of illegal roadblocks and ensure sustained compliance. 2. Continue providing technical support, capacity building, and monitoring to enhance the effectiveness and sustainability of the cooperatives. 3 Maintain regular monitoring and collaborate with relevant regulatory agencies such as NAFDAC, SON, Nigeria Export Promotion Council and KOCCIMA to sustain compliance with export quality standards.
5 | Simplified State and Local business tax regime | 1. Consolidate assessments of rates and levies between State and Local Government. 2. Enlighten the Public on harmonized rates and levies 3. Automate business premises registration and disputes resolution process | 1.The MOU between the KGIRS and the 21 Local Goverment will be redrafted to accomodate the consolidation of assessment of rates and levies. 2. Integration of Business Premises registration and dispute resolution process into the KGIRS portal. 3. Sensitization of the general public on harmonized rates and levies. | 1. Conclude MOU by end of first quarter 2025. 2. Integration done by Second quarter 2025. 3. Monthly town hall sensitisation meetings | KGIRS | Ministry of Local Government and Chieftaincy Affairs. Chairmen of the 21 Local Government & their Director of Local Govts. | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N120,000,000 | 2025-01-01 | 2025-12-31 | COMPLETED visit www.taxpayers.irs.kg.gov.ng for more details | * MOU Concluded in 1st quarter 2025, the Land use charge Law, Signage and advertisement Law was passed and disseminated across all Local government areas. * Monthly town hall meetings successfully conducted across the 21 Local government areas of the State. | Continous sensitization and awareness campaign
6 | Framework for Responsible and Inclusive Land Agricultural Investment (FRILIA) | 1. To enhance tenure governance by offering guidance and information on globally recognized techniques for managing and controlling the rights to use land, fisheries and forests. 2. To optimize transparency and boost efficiency of tenure systems in land intensive agricultural investments | 1. Sensitize stakeholders on globally recognized practices for tenor of land, fisheries and forests 2. Stakeholder engangement to foster continous dialogue and collaborations 3. Setting up greivance management system to address grievances araising from involuntary settlement, valuation, compemsation and others 4. Carry out community needs assesment and prepare community development plans to commit investors to CSR projects and mitigate projects impacts on existing community infrastructure. | 1. Prepare stakeholders engagement plan 2. Sensitization visits to 21 No first class traditional to communicate FRILIA tool kits 3. Identify and analyze stakeholders 4. Identify stakeholders issues and concerns 5. Conduct of 3No sensitization workshop (1No per Senatorial District) to communicate FRILIA tool kits 6. Set up greivance redress committee 7. Carryout community needs assesments in 10No project communities 8. Prepare 10No community development plans 9. Train 20 MoA staff on FRILIA knowledge area | Ministry of Agriculture | Bureau of Lands, KOSIPPPPA, KOGIS | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N150,000,000 | 2025-01-01 | 2025-12-31 | DELAYED | 1.Engagement plan was prepared following FRILIA templates specific to onboarding Mijefa Nigeria Limited, an investor in feed mills. 2. Community assesment was carried out for Ogbetutu Community in Idah Local Government Area. 3. Enagagement of stakeholders was carried out in the community. 4. GRM Committee has been constituted under the Ministry of Agriculture. 5. Actions steps will roll over to 2026 due to delays encountered on some of the key targets Delays was caused due to unforseen cicumstances varying from logistics, communication gaps between the team and members of the communities and resistance from land owners during the sensistisation engagements. | We have rolled over majority of our Action Steps in 2025 Action Plans due to the delays encountered in executiong them we hope to complete these next steps within Jan 2026- Dec 2026 Our next steps is as follows: 1. Sensitization visits to 21 Nos first class traditional to communicate FRILIA tool kits. This exercise is to be completed by December 2026. 3. Identify and analyze stakeholders and addressing their issues and concerns. Timeline Jan-Dec 2026 5. Conduct of 3Nos sensitization workshop (1No per Senatorial District) to communicate FRILIA tool kits. June - Dec 2026 6. Carryout community needs assesments in 10No project communities . 7. Prepare 9Nos community development plans. 8. Train 20 MoA staff on FRILIA knowledge area.
7 | Quick determination of commercial disputes | To Improve significantly the time spent to settle commercial disputes | 1. Establishment of Multi door Court House and more Small claims courts including acquisition of equipments. 2. Employment of skilled professionals and remuneration (at least 4 skilled arbitrators). 3.Remuneration of staff. 4. Public Awareness through Radio, print and electronic media. | 1. Establishments of two small claims courts. 2. Employment of 10 skilled staff. 3. Completion of 5 cases per month | The Judiciary | Ministry of Justice, Ministry of Commerce and Industry, KGIRS and KOCCIMA | Kogi State Chamber of Commerce, Industry, Mines and Agriculture KOCCIMMA. Kogi State NGOs Network KONGONET Kogi State IGBO Traders Association Kogi State Igbo Community Association Nigeria Institute of Estate Surveyors (Kogi Chapter) National Union of Journalist NUJ (Kogi Chapter) Zenith Bank PLC Nigeria Bar Association NBA (Kogi Chapter) Nhub Nigeria Association of National Accountants of Nigeria (Kogi Chapter) | N100,000,000 | 2025-01-01 | 2025-12-01 | DELAYED The Multi door court is yet to commence sittings due to pending accent of the Executive Governor on the bill to set up Mutidoor courts | 1. The Multi Door Court Law has been passed by house of Assembly and awaiting assent by the Governor. 2. Two Small Claims Court have been set up and operational. 3. Atleast 6 cases recorded on monthly basis. 4. More than 70 commercial dispute cases resolved in 2025 . | • To secure 3 more Small Case Court in the State, 1 in each senatorial district by December 2026 • Provision of office equipment and renumeration for judges and other court staffs in the 3rd Quarter of the Year. • Establish 2Nos digitalised small claim courts in the State Capital between July-December 2026 • Provision of enumerations for day to day running of the small claims court. • Employ more skilled staff for the court to ease work load. • Provide of 2Nos utility vehicles for mobility. • Annual capacity Training for staff.