## Sheet1
Ministry, Department, Agency (MDAs) | Project Title | Unique OCID | Project Description | LGA | State | Project Approval Year | Budget Source | Budgeted Amount (N) | Budget Source Url | Tender status | Procurement Method | Procurement Category | Award Criteria | Tender Start Date | Tender End Date | Number of Tenderers | Tenderers (List of Companies ) | Tender Amount (N) | Award ID | Award Status (For projects that the tender did not or have not led to any award) | Award Date | Award Amount | Name of Contractors/ Suppliers | Contract ID | Contract Start Date | Contract End Date | Contract Status | Date Signed | Contract Amount | Transaction Ref/ ID | Amount Paid so far | Payer | Payee | Date(s) of payment [Date 1, Date 2, ...] | Amount Breakdown [amount 1, amount 2, ...] | Procurement Stage
Kogi State Primary Health Care Development Agency(IMPACT Project) | Upgrading of Selected 88 Public Health Centers in Kogi State of Nigeria | ocds-2xftg1-082080-KGS/SPHCDA/010-NG | Upgrading of 22 PHCs in Adavi, Ajaokuta, Idah, Igalamela-odolu, Ogori-magongo LGAs of Kogi State | Adavi, Ajaokuta, Idah, Igalamela-odolu, Ogori-magongo | KOGI | 2024 | WB | 1639975545.24 |  | complete | open | works | MOST RESPONSIVE AND ADVANTAGIOUS BIDDER | 4TH NOVEMBER 2024 | 21ST NOVENBER2024 | 2 | 1. Oysters Holdings Ltd. 2.Multipurpose Errandmen Ltd | 1.1,720,172,700.53 2. 1,613,130,366.00 | KGS/IMPACT/W/01/10/2024/A | active | 2024-12-30 | 1613130366 | MULTI PURPOSE ERRAND MENS SERVICES LTD | KGS/IMPACT/W/01/10/2024/A | 2024-01-11 | 30TH OCT,2025 | active | 2024-01-11 | 1613130366 |  | 1594268773.44 | W/B IMPACT PROJECT | MULTI PURPOSE ERRAND MENS SERVICES LTD | 1. 22/01/2025 2. 17/03/2025 3. 24/04/25 & 08/05/2025 4. 02/06/2025 5. 28/07/2025 6. 07/10/2025 | (1) 478,343,563.85 (2) 318,895,709.23 (3) 263,361,576.60 (4) 199,037,213.66 (5) 113,670,300.64 AND 220,960,409.46
Kogi State Primary Health Care Development Agency(IMPACT Project) | Upgrading of Selected 88 Public Health Centers in Kogi State of Nigeria | ocds-2xftg1-082081-KGS/SPHCDA/011-NG | Upgrading of 22 PHCs in Okehi, Okene, Kabba-bunu, Ijumu LGAs of Kogi State | Okehi, Okene, Kabba-bunu, Ijumu | KOGI | 2024 | WB | 1600996345.61 |  | complete | open | works | MOST RESPONSIVE AND ADVANTAGIOUS BIDDER | 4th NOVEMBER 2024 | 21ST NOVENBER2024 | 3 | 1. Mutual Infrastructure Ltd 2. Millenium Global Resource and services 3. QSA Nigeria Ltd | 1. 3,101,641,788.54 2. 1,640,414,083.08 3. 1,610,747,799.29 | KGS/IMPACT/W/01/10/2024/B | active | 2024-12-31 | 1530210409.33 | QSA NIG. LTD | KGS/IMPACT/W/01/10/2024/B | 2024-01-12 | 30TH OCT,2025 | active | 2024-01-11 | 1530210409.33 |  | 1512374841.29 | W/B IMPACT PROJECT | QSA NIG. LTD | 1.22/01/2025 2. 17/03/2025 3. 08/05/2025 4. 02/06/2025 5. 28/07/2025 6. 08/08/2025 7. 15/10/2025 | (1) 453,755,205.43 (2) 302,503,470.23 (3) 220,889,391.56 (4) 217,740,640.38 (5) 118,612,500.00 (6) 59,296,250.00 AND 139,577,383.69
Kogi State Primary Health Care Development Agency(IMPACT Project) | Upgrading of Selected 88 Public Health Centers in Kogi State of Nigeria | ocds-2xftg1-082082-KGS/SPHCDA/012-NG | Upgrading of 21 PHCs in Lokoja, Mopa-amuro, Yagba east, Yagba west LGAs of Kogi State | Lokoja, Mopa-amuro, Yagba east, Yagba west | KOGI | 2024 | WB | 1619892790.92 |  | complete | open | works | MOST RESPONSIVE AND ADVANTAGEOUS BIDDER | 4th NOVEMBER 2024 | 21ST NOVENBER2024 | 6 | 1. Jedidah Global SynergyNigeria Ltd 2. Inknuel Ltd 3. Armani Investmentand Trust Ltd 4. Munavic Nigeria Ltd 5. Famsaf Construction Company Ltd 6. Kemlude Options Nigeria Ltd | 1. 1,487,500,000.00 2. 1,402,109,764.00 3. Financial bid not included 4. 2,035,000,278.95 5. 1,628,684,951.77 6. 1,664,941,756.00 | KGS/IMPACT/W/01/10/2024/C | active | 2025-01-01 | 1402109764 | INKNUEL LTD | KGS/IMPACT/W/01/10/2024/C | 2024-01-13 | 30TH OCT,2025 | active | 2024-01-11 | 1402109764 |  | 1339682420.42 | W/B IMPACT PROJECT | INKNUEL LTD | 1.22/01/2025 2. 17/03/2025 3. 16/06/2025 4. 24 & 29/11/2025 | (1) 415,769,360.96 (2) 277,179,573.98 (3) 277,178,573.98 (4) 369,554,911.50
Kogi State Primary Health Care Development Agency(IMPACT Project) | Upgrading of Selected 88 Public Health Centers in Kogi State of Nigeria | ocds-2xftg1-082083-KGS/SPHCDA/013-NG | Upgrading of 23 PHCs in Ankpa, Olamaboro, Omala, Ofu, Dekina, Ibaji, Bassa LGAs of Kogi State | Ankpa, Olamaboro, Omala, Ofu, Dekina, Ibaji, Bassa | KOGI | 2024 | WB | 1564927437.24 |  | complete | open | works | MOST RESPONSIVE AND ADVANTAGEOUS BIDDER | 4th NOVEMBER 2024 | 21ST NOVENBER2024 | 2 | 1. Feranmi Greenfield Resources Ltd 2. Base-san Ventures Nigeria Ltd | 1. 1,589,426,538.15 2. 1,545,724,510.78 | KGS/IMPACT/W/01/10/2024/D | active | 2025-01-02 | 1545724510.78 | BASE-SAN VENTURES | KGS/IMPACT/W/01/10/2024/D | 2024-01-14 | 30TH OCT,2025 | active | 2024-01-11 | 1545724510.78 |  | 1069496349.84 | W/B IMPACT PROJECT | BASE-SAN VENTURES | 1. 22/01/2025 2. 17/03/2025 3. 23/07/2025 | (1) 458,355,621.34 (2) 305,570,414.27 (3) 305,570,314.23

## Sheet2 (hidden)
| Activity 2.1.1b.1 | Conduct Annual Engagement of 10 Traditional leaders and other ward level key stakeholders at 220 wards | To engage traditional leaders and stakeholders on awareness and uptake of health services | 1. Identification and invitation of stakeholders 2. Conduction of the meeting 3. report writing and documentation | Strengthened partnership with traditional leaders and key stakeholder | Minutes of meeting | [53 empty] | 7170 | 10038000 | 3513300 | 6524700
| Activity 2.1.1b.2 | Conduct Quarterly sensitization and mobilization of all communities by 3 Ward focal mobilizers (Community Based Health Workers, Town Announcers, Community Volunteers) to 220 HFs and printing of IEC materials | 1. To raise awareness on health services and programs 2. Increase community engagement and participation 3. Promote healthy behaviour | 1. Printing of IEC materials 2. conduct weekly community sensitization sessions in every community 5. Report writing and documentation | 1. Number of communities sensitized 2. Number of IEC materials distributed 3. Number of community engagements held | 1. Community sensitization reports 2. IEC materials distribution records 3. Pre and Post sensitization surveys 4. Community Leaders' feedback | SBCC | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | 32026 | 48039000 | 16813650 | 31225350
| Activity 2.1.1b.3 | Monthly subscription of MIFI modem at 220 HFs | To ensure uninterrupted internet connectivity for health facilities | Payment of monthly subcription allowance | Reliable and consistent internet connectivity for HF | Payment receipts | [53 empty] | 4302 | 6453000 | 2258550 | 4194450
| Activity 2.1.1b.4 | Quarterly Purchase of essential drugs/commodities (RDT,ACT,SP) at 220 HFs to address the low testing rate and ACT/SP use among under 5 chlidren and pregnant women | 1. To aid in prompt diagnosis and treatment of malaria among children under 5 and pregnant women | Purchase of RDT, ACT and SP | Increased number of testing and treatment of malaria among children under 5 and pregnant women | 1. Purchase receipts and invoice | [53 empty] | 28680 | 43020000 | 15057000 | 27963000
| Activity 2.1.1b.5 | Production of a booklet of GRM and Environment waste management checklist by all 220 Health Facilities | 1. To enhance patient satisfaction through effective grievance redress 2. to improve waste management practices in health facilities | 1. 1-day Orientation of HF staff on checklist usage 2. Printing of Checklist booklets by HFs 3. Report writing and documentation | 1. Number of HFs equipped with GRM checklist 2. Number of HFs equipped with WM checklist | 1. Facility staff orientation report 2. Patient satisfaction survey 3. facilityn assessment report | E&SSO | [52 empty] | 7010.6667 | 10516000 | 3680600 | 6835400
| Activity 2.1.1b.6 | Engagement of 1 SBA to 220 HFs on Ad-hoc | To improve maternal and newborn healthcare services | 1. Selection and recruitment 2. Ad-hoc engagement | 1.Improved access to SBA 2. Enhanced confidence in HF | 1. Recruitment and engagement records 2. Facility delivery records | [53 empty] | 101973.3333 | 152960000 | 53536000 | 99424000
| Activity 2.1.1b.7 | Monthly Incentivization of 2 TBAs per ward on refferrals at 220 HFs | To Improve MNCH Service provision | 1. Incentivization of HCWs/HFs for service delivery 2. Incentivization of TBAs for referrals to HFs | 1. Improved service delivery by healthcare workers and health facilities 2. Increased referrals from TBAs to HFs 3. Enhanced collaborations between HCWs, HFs and TBAs | 1. HCW/HF/TBA incentive records and payment receipts 2. TBA referral records and tracking sheets 3. Observations for ISS | RMNCAH+N CM | [52 empty] | 28680 | 43020000 | 15057000 | 27963000
| Activity 2.1.1b.8 | Monthly incentivization of 6 mothers per HF after delivery across the 220 health facilities | To increase the number of mothers delivering in health facilities by providing incentives and promoting a culture of safe childbirth practices | 1. Procurement of mama kits (Incentives) 2. Report writing and documentation | 1. Increased number of facility-based deliveries 2. Improved maternal and newborn outcomes 3. Enhanced client satisfaction | 1. Facility delivery records and reports 2. Observations by supervisors | RMNCAH+N Case Manager | [52 empty] | 172080 | 258120000 | 90342000 | 167778000
| Activity 2.1.1b.9 | Augument monthly allowances of 1 Engaged Adhoc Medical Record Officer per facility with N20,000 at the 220 HFs | To strenghthen HMIS, enhancing data quality and support informed decision-making | 1. Review of engaged MROs 2. Monthly payment of allowances | 1. Improved data quality and accuracy in health facilities 2. Increased efficiency in health facility operations | 1. Review reports of MROs 2. Health facilty data quality and accuracy assessments | M&E | [52 empty] | 28680 | 43020000 | 15057000 | 27963000
| Activity 2.1.1b.10 | Conduct 1-day quarterly integrated medical outreach, one per ward (prioritizing the underserved communities) across the 220 wards | To improve healthcare access and services in underserved communities through quarterly integrated medical outreach | 1. Procurement of outreach commodities 2. Planning meeting 3. Mobilization of senior supervisors 4. Community mobilization and sensitization 5. Conduct of 3-day outreach exercise 6. Report writing and documentation | 1. Enhanced healthcare access for underserved population 2. strengthened referral systems 3. Documented outreach reports and lessons learnt | 1. Outreach report and data 2. Community feedback | RMNCAH+N Case Manager | [52 empty] | 9560 | 14340000 | 5019000 | 9321000
| Activity 2.1.1b.11 | Conduct one day quarterly meeting for harmonization of financial records by 5 officers (WDC Members with HF staff) | To ensure accuracy and consistency of financial records | 1. Planning meeting 2. Carry out meeting by 5 officers | 1. Accurate and consistent financial records 2. Improved Financial Management 3. Action plans | 1. Meeting attendance records 2. Action plans documentation 3. Financial record review reports | [53 empty] | 9560 | 14340000 | 5019000 | 9321000
| Activity 2.1.1b.12 | Provision of Grievance boxes at 220 HF | To encourage grievance reporting and mitigating issues that may occur on the project |  | Number of grievance and feedback collected | Grievance report | SSO | [53 empty] | 1433960 | 501886 | 932074
|  | Sub Total | [57 empty] | 460928.5429 | 645299960 | 225854986 | 419444974
| Activity 2.2.1.1 | Conduct a 3-Day Quarterly Quality Assessment visit by 45 trained quality assesors to 120 HCFs | 1. To evaluate HF QoC 2. To identify areas of improvement 3. to enhance service delivery | 1. Planning meeting of quality assessors 2. Conducting 3 days quality assessment 3. Provide feedback and recommendation 4. Report writing and documentation | 1. Number of HF assessment conducted 2. Quality improvement plan developed 3. Enhanced health service delivery | 1. Assessment reports 2. HF evaluation scores 3. Quality improvement plans | PM/RMNCAH+N CM | [11 empty] | X | [13 empty] | X | [12 empty] | X | [12 empty] | x | 23922.1429 | 33491000.01 | 11721850.0035 | 21769150.0065
Sub-Component 2.2.1: Health systems strengthening and technical assistance | Activity 2.2.1.2 | Support the conduct of 1-day Quarterly State Steering Committee Meeting for 15 people | 1. To guide program implementation 2. Ensure stakeholder engagement 3. Monitor progress | 1. Conduct of Quarterly State Steering Committee Meeting for 15 people 2.Report writing and documentation | 1. Informed decision making 2. Enhanced stakeholder collaboration 3. Program implementation guidance | 1. minutes of meeting and attendance | PM | [51 empty] | x | 517.8571 | 725000 | 253750 | 471250
| Activity 2.2.1.3 | Support conduct of 3-day Quarterly PHC Integrated Supportive Supervision (inclusive of E&SS activities) by 45 senior supervisors | 1. Enhance PHC service quality 2. Ensure E&SS compliance | 1. Planning meeting of PHC ISS Supervisors 2. Conducting 3 days PHC ISS Bi-Monthly 3. Provide feedback and recommendation 4. Report writing and documentation | 1. Improved PHC service delivery 2. Enhanced E&SS compliance | 1. Supervision reports 2. Copy of feedback template 3. E & SS monitoring reports | RMNCAH+N/IMM Case Manager | [5 empty] | X | [7 empty] | X | [8 empty] | X | [8 empty] | X | [8 empty] | X | [7 empty] | X |  |  |  | 17460 | 24444000 | 8555400 | 15888600
| Activity 2.2.1.4 | Conduct 2-days quarterly mentoring of targetted HFs on defaulter tracking on Routine immunization, by 42 state officers considering the poor current status (7.5%) of Fully immunized children in the State. | To improve Routine immunization coverage in identified missed settlements | 1. Identification of targeted health facilities 2. Development and printing of mentoring tools and guides 3. Quarterly menteroring sessions 4. On-site coaching and support 5. Data analysis and feedback provision 6. Report writing and documentation | 1. Enhanced defaulter tracking and management 2. Increades identification of missed opprtunities 3. Improved routine immunization coverage 4. Documented progress reports | 1. Mentoring session records 2. Defaulter tracking records 3. Missed opportunity identification records 4. Immunization coverage metrics 5. Health facility evaluation forms 6. Quarterly progresss report | IMM/M&E | [52 empty] | 8100 | 11340000 | 3969000 | 7371000
|  | SUB TOTAL | [57 empty] | 50000 | 70000000.01 | 24500000.0035 | 45500000.0065
Sub-Component 2.2.2: SPHCDA TA, operations and performance framework payments through performance contracts | Activity 2.2.2.1 | Annual Maintenance Fee of Flexible Accounting software package | 1. Ensure software reliability and stability 2. Maintain optimal accounting functionality 3. Enhance financial data Security | 1. Annual software license renewal 2. Technical support and maintenance services 3. software update and upgrade 4. Report writing and documentation | 1. Continuous software availability 2. Accurate financial reporting 3. Enhanced data security | 1. Software functionality checks 2. Error and issue tracking 3. Financial report accuracy | PM/PROJECT ACCOUNTANT | [43 empty] | x |  |  |  | x |  |  |  |  | 357.1429 | 500000 | 175000 | 325000
| Activity 2.2.2.2 | Quarterly financial audits of PHCs, LGHAs | 1. Ensure financial transparency and accountability 2. Identify and mitigate financial risk 3. Improve financial management and compliance | 1. Planning meeting 2. On-sight audit and data collection 3. Audit report writing and presentation 4. Follow up and implementation monitoring | 1. Quarterly Audit reports 2. Improved financial management practices | 1. Audit report and verification 2. Financial statement accuracy | AUDITOR | [51 empty] | x | 9780 | 13692000 | 4792200 | 8899800
| Activity 2.2.2.3 | Annual conduct of 1 week external audit to the state | 1. Enhance financial accountability and transparency 2. Enhanced operational efficiency and effectiveness 3. Improved compliance with regulatory requirements | 1. Engagement of External Audit firm 2. Planning meeting on scope definition 3. On-sight audit and data collection 4. Audit report writing and presentation 5. Follow up and implementation monitoring | 1. Independent audit reports 2. Identified areas for improvement 3. Enhanced financial management practices | 1. Audit report and verification 2. Financial statement accuracy | PM/AUDITOR | [51 empty] | x | 10714.2857 | 15000000 | 5250000 | 9750000
| Activity 2.2.2.4 | Conduct 3-day quarterly LGA PHCAs performance framework assessment using national standardized checklist by 21 state officials | To evaluate LGHA performance via standardized assessment, driving health service delivery improvement | 1. Provide support to LGHA to develop a realistic activity plan 2. Development of standardized checklist 3. Planning meeting 4. On-sight assessment and data collection 5. Data analysis and report writing 6. Stakeholder feedback and validation 7. Report disemmination and follow up | 1. Comprehensive assessment report 2. Identified performance gaps 3. Improved health service delivery | 1. Assessment reports 2. Validation from stakeholders 3. Implemetation of recommendations | PM/ACCOUNTANT | [52 empty] | 4911 | 6875400 | 2406390 | 4469010
| Activity 2.2.2.5 | Conduct 1-day monthly integrated review meeting for 5 LGA team members and partners on programme performance | To improve healthcare programme performance in all LGAs | 1. Planning meeting 2. Conduct planning meeting 3. Report writing and documentation | [55 empty] | 17113.9643 | 23959550 | 8385842.5 | 15573707.5
| Activity 2.2.2.6 | Payment of annual rent for IMPACT Office | Secure IMPACT office space through timely rent payments | Rent payment process | Continous office occupancy | Rent payment receipt | PM/Project Accountant | [52 empty] | 1428.5714 | 2000000 | 700000 | 1300000
| Activity 2.2.2.7 | Communication & Monthly data MODEM recharge for State/LGA HMIS Officers. | Ensure seamless HMIS data management through reliable communication and internet connectivity | Monthly Data recharge | Uninterrupted internet connectivity | Data recharge records | M&E | [43 empty] | x |  |  |  | x |  |  |  |  | 1221.4286 | 1710000 | 598500 | 1111500
| Activity 2.2.2.8 | Support 21 state personnel to participate in data validations meetings at the LGAs/Wards | Enhance data accuracy through state personnel participation in LGA data validation meeting | 1. Planning meeting 2. Deploy personnel for data validation 3. Report writing and documentation | Validated health data | 1. Meeting attendance records 2. Data validation reports | M&E | [52 empty] | 10800 | 15120000 | 5292000 | 9828000
| Activity 2.2.2.9 | Conduct 1-day Monthly PIU Meetings for 11 members | 1. Enhance program coordination and implementation 2. Foster collaboration among team members 3. monitor progress and address challenges | 1. Conduct Monthly PIU Meetings for 11 members 2. Report writing and documentation | 1. Improved program coordination, implementation, team collaboration and communication 2. Timely issues resolution and decision making | 1. minutes of meeting and attendance | PM |  | X |  |  |  | X | [5 empty] | X | [6 empty] | X |  |  |  | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  | x | 514.2857 | 720000 | 252000 | 468000
| Activity 2.2.2.10 | Monthly Payment of Operational Budget for SPHCB PIU | 1. Ensure timely funding for PIU operations 2. Support effective program implemetation | 1. Send budget for review and approval 2. Disburse funds quarterly 3. Monitor expenditure 4.Report writing and documentation | 1. timely payments of PIU operational costs 2. Effective program implementation | 1. Payment records 2. Budget expenditure report 3. PIU activity reports | PM/Project Accountant | X |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  | X |  |  |  | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  |  | X |  |  |  | X |  |  |  | X |  |  |  | x | 32142.8571 | 45000000 | 15750000 | 29250000
| Activity 2.2.2.11 | Support payment of operational expenses to the PFMU | 1. Ensure timely funding for PFMU 2. Support effective program implemetation | 1. Send budget for review and approval 2. Disburse funds quarterly 3. Monitor expenditure 4.Report writing and documentation | 1. timely payments of PFMU and operational costs 2. Effective program implementation | 1. Payment records 2. Budget expenditure report 3. PFMU activity reports | PM/Project Accountant | [51 empty] | x | 4950 | 6930000 | 2425500 | 4504500
| Activity 2.2.2.12 | Community Client Satisfaction Survey (CCSS) | To ascertain clients satisfaction encompassing prevalences, findings, suggestions and recommentation on service delivery | [56 empty] | 2835 | 3969000 | 1389150 | 2579850
| Activity 2.2.2.13 | Monitoring and supervision of upgrade of health facilites across the State | To ensure the timely effective and efficient upgrade of Health Facilities across the state | 1. Conduct of regular site visits to undergoing upgrade 2. Review and analyse progress report from contractors | 1. Timely and accurate progress report. 2. Verification record | [54 empty] | 3231.4286 | 4524000 | 1583400 | 2940600
|  | SUB-TOTAL | [57 empty] | 99999.9643 | 139999950 | 48999982.5 | 90999967.5
Sub-Component 2.2.2b End of Project Closure Activity | Activity 2.2.2b | End of project closure activity | Proper documentation and dessemination of project achievements | [56 empty] | 100000 | 140000000 | 49000000 | 91000000
Sub - Componenet 2.2.3 PIU performance framework | Activity 2.2.3 | Provision of Non-Monetary incentives to SPHCDB PIU | 1. Motivate and recognise outstanding performance 2. Enhance staff moral and job satisfaction 3. Boost program implementation efficiency | 1. Provision of professional development opportunities (trainings and workshop) 2. Celebration of milestones and achievements (award ceremonies) 3. Strategic retreats for team building and goal setting 4. Report writing and documentation | 1. Improved staff motivation and morale 2. Enhanced productivity and efficiency 3. Better quality service deliver 4. Documented incentive distribution reports | 1. Staff feedback and satisfaction surveys 2. Retreat evaluation report | PM | [52 empty] | 50000 | 70000000 | 24500000 | 45500000
Sub-Component 2.3: LGHA operations and performance framework payments through performance contracts | Activity 2.3 | LGHA operations, a performance framework payments through performance contracts | To enhance LGHA performance through incentive-based operational support | 1. Performance framework development 2. 2. LGHA assessment and scoring 3. Incentive payment process | 1. Improved LGHA performance 2. Enhanced service delivery 3. Increased accountability 4. Standardized performance measurement 5. Documented performance improvement plans | 1. Payment records 2. LGHA performance reports 3. Assessment and scoring documents | PM/PROJECT ACCOUNTANT | [42 empty] | x |  |  |  |  | x |  |  |  | x | 160369 | 224516600 | 78580810 | 145935790
[61 empty] | 1219816510.01 |  | 838380731.5065